## Slide 1: Software Project Management Life Cycles, Planning & Agile Methods
Week 3 · Lecture 2 | Life Cycles, Planning, Agile, Scrum & Kanban
FALL 2026
Dr. Anam Mustaqeem
anam.mustaqeem@ucp.edu.pk
Office: Cabin #2, F303 Building A
OFFICE HOURS: Wednesday : 09:00 AM- 12:00 PM
Thursday: 09:00 AM- 11:00 AM

## Slide 3: Today’s Agenda
Product and project life cycles
Phases of a project, process groups and phase gates
Software project planning and the Step Wise framework
Introduction to Agile: the Manifesto and its principles
The Scrum framework: accountabilities, events and artifacts
Kanban: visualising work and limiting WIP
Choosing an approach: Scrum, Kanban or plan-driven
Five in-class activities along the way

## Slide 4: Product and Project Life Cycles
Part 1 | Two different things that are routinely confused

## Slide 5: Project Vs Product
PROJECT
A temporary endeavour undertaken to create a unique product, service or result.
Has a definite start and a definite end
Ends when objectives are met, or cannot be met
Repeating an identical build is operations, not a project
Success: scope, time, cost and quality
PRODUCT
An artefact that is produced, is quantifiable, and can be an end item or a component.
Persists after the project that created it closes
Is maintained, extended and eventually retired
Usually outlives several projects and teams
Success: adoption, value and total cost of ownership

## Slide 6: A Product Life Cycle Contains Many Project Life Cycles
Introduction
Growth
Maturity
Decline
Retirement
Project A
Initial build and v1.0 release
Project B
Mobile client added
Project C
Payments integration
Project D
Platform migration
Project E
Decommission and data export
WHAT THIS MEANS FOR THE PROJECT MANAGER
Your project inherits decisions made by earlier projects
Your decisions constrain projects that have not started yet
Handover to operations is part of your scope, not an afterthought
WHERE AGILE CHANGES THE PICTURE
Many agile organisations keep a standing product team that owns the product for its whole life, with no project start or end to manage. This is the “project to product” shift.

## Slide 7: Phases of a Project
Part 2 | Process groups, phases and what a phase gate is for

## Slide 8: The Five Process Groups
1
Initiating
Authorise the project
Business case and feasibility
Project charter
Identify stakeholders
2
Planning
Define how it will be done
Scope, WBS, schedule, budget
Risk, quality and resource plans
The baseline
3
Executing
Do the work
Build the deliverables
Lead and develop the team
Engage stakeholders
4
Monitoring & Controlling
Compare and correct
Track against the baseline
Change control
Runs alongside all others
5
Closing
Finish deliberately
Formal acceptance, handover
Release resources
Capture lessons learned

## Slide 9: Phases, Deliverables and Gates
Feasibility
Business case
Requirements
Requirements spec
Design
Architecture & design
Build
Tested components
Deploy
Live system
◆ = phase gate: a deliverable is reviewed and a decision is made
WHAT A GATE DECIDES
Proceed to the next phase
Proceed with conditions attached
Return to the previous phase and rework
Terminate the project

## Slide 10: Activity : Make the Gate Call
SCENARIO: CAMPUSRIDE APP
Your team is building a shuttle-tracking app for the university’s Transport Office. You have reached the gate at the end of the Design phase.
The design is complete, well reviewed and the team is proud of it
Revised estimate: cost is now 60% above the business case
Yesterday, the Transport Office announced it will replace campus shuttles with a contracted bus service from next year
The team has already spent four months on the project
YOUR CALL
Vote. Be ready to defend it.
1
Proceed
2
Proceed with conditions
3
Rework: go back a phase
4
Terminate

## Slide 11: Software Project Planning
Part 3 | What planning is, what it produces, and a structured method for doing it

## Slide 12: Defining the Planning Process
WORKING DEFINITION
Planning is deciding what must be done, in what order, by whom, with what resources and by when, and recording those decisions so progress can be measured against them.
WHAT PLANNING PRODUCES
Scope statement and work breakdown structure
Schedule with dependencies and critical path
Cost estimate and budget baseline
Resource and staffing plan
Risk register with owners and responses
Quality criteria and communication plan
1
It is iterative
The plan is revised whenever new evidence arrives. A plan never updated is a historical document.
2
It is progressively elaborated
Near-term work is planned in detail, distant work coarsely: rolling wave planning.
3
It creates a baseline
Without a recorded baseline there is nothing to measure schedule or cost variance against.

## Slide 13: How Much Can You Plan Up Front?
1
Predictive
Plan the whole project up front
Use when: Requirements are stable and well understood
2
Iterative
Plan the whole; refine the solution in cycles
Use when: The problem is understood; the solution is not
3
Incremental
Plan releases; deliver usable pieces
Use when: Value can be delivered before everything is finished
4
Adaptive (Agile)
Plan the next iteration in detail, the rest coarsely
Use when: Requirements will be discovered during the work
More certainty · more up-front planning
More uncertainty · more re-planning
COMMON MISCONCEPTION “Agile means less planning.” It means more planning events at shorter intervals, with less wasted planning. Agile moves planning; it does not remove it.

## Slide 14: Introduction to Agile
Part 4 | Where it came from, what it actually says, and where it does not apply

## Slide 15: The Agile Manifesto: Four Values
1
Individuals and interactions
over processes and tools
A capable team with a weak process beats a weak team with a strong one.
2
Working software
over comprehensive documentation
Running code is the honest measure of progress.
3
Customer collaboration
over contract negotiation
The customer is a participant in the project, not the other side.
4
Responding to change
over following a plan
A plan is a forecast, revised as evidence arrives.

## Slide 16: The Twelve Principles in Four Groups
A
Customer value
Satisfy the customer with early, continuous delivery
Welcome changing requirements, even late
Deliver working software often: weeks, not months
Working software is the primary measure of progress
B
Collaboration
Business people and developers work together daily
Prefer face-to-face conversation
Build projects around motivated individuals, and trust them
C
Sustainability
Keep a pace the team can sustain indefinitely
Continuous attention to technical excellence and good design
Simplicity: maximise the work not done
D
Self-improvement
The best designs emerge from self-organising teams
At regular intervals the team reflects and adjusts

## Slide 17: Plan-Driven and Agile Side by Side
 | Plan-driven | Agile
Requirements | Defined up front and baselined | Emerge; a prioritised, changing backlog
Planning | Detailed plan for the whole project | Detailed for the next iteration, coarse beyond
Change | Controlled by a formal change process | Expected; re-prioritised each iteration
Delivery | Usually once, at the end | Working increments at a fixed interval
Documentation | Comprehensive, before build | Enough to build and to maintain
Team | Specialised roles, assigned tasks | Cross-functional and self-managing
Success measure | Conformance to the baseline | Working software and delivered value
Fails when | Requirements turn out to be wrong | Certification or fixed contract scope is required

## Slide 18: Activity 2: Agile Myth or Fact?
1
Agile means you don’t write documentation.
2
Agile teams plan more often than plan-driven teams.
3
Agile welcomes changing requirements, even late in development.
4
The Agile Manifesto rejects contracts with customers.
5
Agile is always the best choice for a software project.

## Slide 19: The Scrum Framework
Part 5 | Three accountabilities, five events, three artifacts and the loop they serve
Notes: Source: The Scrum Guide (2020).

## Slide 20: How a Sprint Runs
Product Backlog
Ordered by the Product Owner
Sprint Planning
Goal agreed, items selected
Sprint (2-4 weeks)
Daily Scrum every day
Sprint Review
Increment inspected with stakeholders
Retrospective
The process itself is improved
↻ The loop repeats at a fixed cadence: inspect, then adapt
1
Transparency
The work and its state are visible to everyone who inspects it. A hidden problem cannot be fixed.
2
Inspection
Progress toward the goal is checked often, but not so often that checking gets in the way of the work.
3
Adaptation
If inspection shows a deviation, adjust now, not at the next stage gate.

## Slide 21: Three Accountabilities and How Each One Fails
PO
Product Owner
Maximises the value of the product. Owns the Product Backlog: content, order and clarity. One person, not a committee.
ANTI-PATTERN
A proxy with no real authority, so every decision escalates and the backlog stalls.
SM
Scrum Master
Makes the team effective. Coaches the framework, removes impediments and protects the team from mid-sprint disruption.
ANTI-PATTERN
Acting as a project manager who assigns tasks and chases status.
D
Developers
Create a usable increment every sprint. Self-managing: they decide how the work is done and who does what.
ANTI-PATTERN
Narrow specialists, so work piles up behind one person.

## Slide 22: Five Events: Timeboxed Inspect-and-Adapt Points
Event | Timebox* | Purpose | The point people miss
The Sprint | ≤ 1 month | Container for all other events; fixed length | Caps risk at one sprint’s cost
Sprint Planning | ≤ 8 hours | Agree the Sprint Goal, select items, plan the work | Why valuable? What? How?
Daily Scrum | 15 min | Developers inspect progress and adapt the day’s plan | A planning event, not a status report
Sprint Review | ≤ 4 hours | Inspect the increment with stakeholders; decide next steps | A working demo, not slides
Sprint Retrospective | ≤ 3 hours | Inspect how the team worked; commit to improvements | The only event about process, not product

## Slide 23: Three Artifacts, Each With a Commitment
1
Product Backlog
An ordered, emergent list of everything that could improve the product. Never complete.
COMMITMENT: Product Goal
The long-term objective the team works toward.
2
Sprint Backlog
Items selected for this sprint plus the plan to deliver them. Owned by the Developers.
COMMITMENT: Sprint Goal
One objective; lets the team renegotiate scope without losing purpose.
3
Increment
A usable step toward the Product Goal. Several may be created in one sprint.
COMMITMENT: Definition of Done
The shared quality bar. Not met means not done.
A weak Definition of Done is the usual cause of “we finished the sprint but nothing shipped”.

## Slide 24: Activity: Who Owns It?
a
Deciding which feature goes to the top of the backlog
b
Another department keeps pulling a developer away mid-sprint
c
Splitting a story into tasks and deciding who takes which
d
Explaining to stakeholders what the next release will contain
e
Coaching the team to run a more useful retrospective
f
Making sure the increment actually meets the Definition of Done
SHOW YOUR ANSWER
1
Product Owner
2
Scrum Master
3
Developers

## Slide 25: Kanban
Part 6 | The other control: limit work in progress instead of timeboxing it

## Slide 26: Kanban: Visualise the Work, Then Limit It
Backlog
Analysis
3
Development
3
Review
2
Done
Development is at its WIP limit of 3: nothing new may enter.
CORE PRACTICES
1. Visualise the workflow as it really is
2. Limit work in progress (WIP)
3. Manage flow: measure cycle time, fix bottlenecks
4. Make policies explicit (what does “ready for review” mean?)
The Kanban Method adds two more: implement feedback loops, and improve collaboratively.
No sprints. No prescribed roles. Work is pulled, not pushed.

## Slide 27: Why Limiting WIP Works: Little’s Law
Average cycle time = Work in progress ÷ Throughput
TEAM A
WIP = 10 items
Throughput = 2 items / day
Cycle time = 5 days
TEAM B
WIP = 4 items
Throughput = 2 items / day
Cycle time = 2 days
PULL, NOT PUSH
Same team, same speed: fewer items in progress means each item finishes sooner.
When a column is full, the person who is free helps clear the next column instead of starting new work.

## Slide 28: Choosing Between Scrum and Kanban
 | Scrum | Kanban
Cadence | Fixed-length sprints | Continuous flow
Commitment | A Sprint Goal per sprint | No sprint-level commitment
Roles | PO, SM, Developers | None prescribed
Mid-cycle change | Protect the Sprint Goal | Re-prioritise any time
Typical metric | Velocity (common practice) | Cycle time, throughput
Best fit | Feature work with a plannable backlog | Support and maintenance work
SCRUMBAN
Keep Scrum’s events and roles; add WIP limits and pull inside the sprint.
WHEN NEITHER FITS
Safety-critical or certified systems
Fixed-price, fixed-scope contracts
Hardware with long lead times
Truly stable requirements

## Slide 29: Activity : Match the Approach to the Project
A
Hospital radiotherapy module. Must be certified before clinical use; requirements come from a clinical standard.
B
Three-person startup building a food-delivery app. No customers yet; the core feature changes every month.
C
University payroll migration to a new system with the same rules. The team has done two similar migrations.
D
In-house team maintaining 12 internal systems. Work arrives as tickets, from 10 minutes to 2 weeks long.
YOUR TASK (TRIOS)
Pick for each: Predictive, Scrum, Kanban or a hybrid.
Justify with one constraint from the scenario.
For the hardest one: what single fact would change your answer?

## Slide 30: Exit Ticket
Your FYP: predictive, Scrum or Kanban?

## Slide 31: Conclusion
A product outlives the projects that build it; your project inherits and imposes constraints.
A phase gate is only useful if stopping the project is a real option.
Planning is reasoning, not a Gantt chart: iterative, progressively elaborated, baselined.
Agile moves planning; it does not remove it.
Scrum timeboxes the work; Kanban limits it. Both are inspect-and-adapt controls.
Choose by the shape of the work and its uncertainty, not by what sounds modern.