## Slide 1: Software Project Management An Overview of Project Planning: The Step Wise Method
Week 3 · Lecture 3 | Chapter 3, Software Project Management (Hughes & Cotterell)
FALL 2026
Dr. Anam Mustaqeem
anam.mustaqeem@ucp.edu.pk
Office: Cabin #2, F303 Building A
OFFICE HOURS: Wednesday : 09:00 AM- 12:00 AM
Thursday: 09:00 AM- 11:00 PM
Notes: Week 3, Lecture 2. Source: Hughes & Cotterell, Software Project Management, Chapter 3: An Overview of Project Planning (Step Wise).

## Slide 2
Notes: Opening dua.

## Slide 3: Today’s Agenda
Introduction to Step Wise project planning
Case study: Brigette at Brightmouth College
Steps 0–3: select the project, set scope, infrastructure and approach
Steps 4–6: products and activities, effort estimates, activity risks
Steps 7–10: resources, review, execution and lower levels of planning
In-class activities on the case study
Summary
Notes: Original 'Contents' slide, expanded to show the parts of the lecture.

## Slide 4: Introduction to Step Wise
Part 1 | A framework of basic steps in project planning

## Slide 5: Introduction to Step Wise project Planning
This section describes a framework of basic steps in project planning on which the following course contents are build.
The described framework is called the Step Wise Method.

## Slide 6: Step Wise Planning: Overview
0. Select project
1. Identify scope and objectives
2. Identify infrastructure
3. Analyse project characteristics
4. Identify products and activities
5. Estimate effort for each activity
6. Identify activity risks
7. Allocate resources
8. Review / publicise plan
10. Lower-level planning
9. Execute plan
For each activity
Review
Lower-level detail
READING THE DIAGRAM
Steps 0–4 frame the project.
Steps 5–8 (dashed box) build the detailed plan; 5–6 repeat for each activity.
Steps 9–10 loop back as the project runs, re-planning in more detail.
Step 3 decides the overall approach.
Notes: Original slide 4 (was an image of the book's Figure 3.1), redrawn so it is sharp on a projector and editable.
Walk the diagram top to bottom. Point out the two loops: 'for each activity' (steps 5–6) and the loop from step 10 back up to step 4 (review) and into the detailed planning box (lower-level detail).

## Slide 7: Case Study
Brigette has been working for the management services department of a local authority when she sees an advertisement for the position of information systems development officer at brightmouth college. She is attracted to the idea of being her own boss, working in a relatively small organization and helping them to setup appropriate information systems from scratch. She applies for the job and get it. One of the first tasks that confronts her is the implementation of independent payroll processing.

## Slide 8: Steps 0–3: Setting the Frame
Part 2 | Select the project, set scope and objectives, infrastructure and approach

## Slide 9: Step 0: Select Project
Called Step 0 because it is actually outside the main project planning steps.
While feasibility study suggests that there is a business case for the project, it would still need to be established that it should have priority over other projects.
This evaluation can be part of project portfolio management.

## Slide 10: Step 1: Identify Project Scope and Objectives
1.1 Identify objectives and practical measures of the effectiveness in meeting those objectives
1.2 Establish a project authority
1.3 Stakeholder analysis – identify all stakeholders in the project and their interests
1.4 Modify objectives in the light of stakeholder analysis
1.5 Establish methods of communication with all parties

## Slide 11: Step 1: Identify Project Scope and Objectives
Activity 1:
  List objectives and
  Identify the main stakeholders and project authority in the provided scenario.

## Slide 12: Case Study
Project Authorities: Brigette finds that effectively she has two different clients for the payroll system: the finance and human resources departments. To help resolve conflicts, it is agreed that the managers of both departments should attend a monthly meeting with the vice-principal which Brigette has arranged in order to steer the project.
Following are the ‘objectives’
  to implement the new application on time and within budget;
  to implement the new software application with the fewest possible software errors that might lead to operational failures;
  to design a system that is user-friendly;
  to produce full documentation for the new system.

## Slide 13: Step 2: Identify Project Infrastructure
Identify relationship between the project and strategic planning
Identify installation standards and procedures
Identify project team organization

## Slide 14: Activity 2: List some standards that brigette should identify and set before moving on further
Brigette at Brightmouth College finds that there is an overall College strategic plan which describes new courses to be developed, and so on, and mentions in passing the need for ‘appropriate administrative procedures’ to be in place. There is a recommendation in a consultant’s report concerning the implications of financial autonomy that independent payroll processing be implemented as just one module in an ERP system which would cover all the college’s financial processing needs. Although the college has quite a lot of ICT equipment for teaching purposes, there is no machine set aside for payroll processing and the intention is that the hardware to run the payroll will be acquired at the same time as the software.
Brigette finds no documents except for some handouts for students that have been produced by different lecturers at different times and which seem to contradict each other. As a stop-gap measure, Brigette writes a brief document which states what the main stages of a ‘project’ (perhaps ‘job for the user’ would be a better term in this context) should be. She stresses that:
● no job of work to change a system or implement a new one is to be done without there being a detailed specification first
● the users must record agreement to each specification in writing before the work is carried out.
She draws up a simple procedure for recording all changes to user requirements.

## Slide 15: Step 3: Analyze Project Characteristics
Distinguish the project as either objective- or product-driven
Analyze other project characteristics
Identify high-level project risks
Take into account user requirements concerning implementation
Select development methodology and life- cycle approach
Review overall resource estimates

## Slide 16: Step 3: Analyze Project Characteristics
Activity 3: Prepare a list of risks, that you think brigette will identify in this step.

## Slide 17: Steps 4–6: Products, Effort and Risks
Part 3 | From deliverables to activities, estimates and activity risks

## Slide 18: Step 4: Identify Project Products & Activities
Identify and describe project products- Work Breakdown Structure
Document generic product flows
Recognize product instances
Produce ideal activity network
Modify the ideal to take into account need for stages and checkpoints

## Slide 19: Step 4: Identify Project Products & Activities
Activity 4: Identify products and activities performed.

## Slide 20: Step 4: Identify Project Products & Activities
Activity 4:
Brigette at Brightmouth College has no installation standard PBS, although she can, of course, refer to various books for standard checklists. She decides that one part of the PBS should contain the products needed to help select the appropriate hardware and software for the payroll application
At brightmouth college, Brigette has decided that the finance department at the college should carry out acceptance testing of the new payroll system. The staff are not sure what test documents should look like, Brigette draws up a product description of a test case. Write the content for this product description.

## Slide 21: Step 5: Estimate Effort for Each Activity
Carry out bottom-up estimates
Revise plan to create controllable activities

## Slide 22: Step 6: Identify Activity Risks
Identify and quantify activity-based risks
Plan risk reduction and contingency measures where appropriate
Adjust overall plans and estimates to take account of risks
Activity 5: Brigette identifies as a risk the possible absence of key staff when investigating the user requirements, as this activity will take place over the holiday period. How can she reduce this risk?

## Slide 23: Steps 7–10: Resources to Execution
Part 4 | Allocate resources, agree the plan, then plan in more detail

## Slide 24: Step 7: Allocate Resources
Identify and allocate resources
Revise plans and estimates to take into account resource constraints

## Slide 25: Step 8: Review/Publicize Plan
Review quality aspects of the project plan
Document plans and obtain agreement

## Slide 26: Steps 9/10: Execute Plan/Lower Levels of Planning
Once the project is under way, plans will need to be drawn up in greater detail for each activity as it becomes due.
Detailed planning of the later stages will need to be delayed because more information will be available nearer the start of the stage.
It is necessary to make provisional plans for the more distant tasks.

## Slide 27: Activity 6
List the products created by the step wise planning process.

## Slide 28: Summary
Any planning approach should have the following elements:
  the establishment of project objectives
  the analysis of the characteristics of the project
  the establishment of an infrastructure consisting of an appropriate organization and set of standards, methods and tools
  the identification of the products of the project and the activities needed to generate those products
  the allocation of resources to activities
  the establishment of quality controls
  Project planning is an iterative process
  As the time approaches for particular activities to be carried out they should be re-planned in more detail.

## Slide 29: Reading
[Chapter 3] “Software Project Management by Bob Hughes and Mike Cotterell, McGraw-Hill Education; 6th Edition (2009). ISBN-10: 0077122798”