## Slide 1: Agile Scrum in Jira
Milestone 1 · SESE4143 Software Re-engineering
Taimoor Hassan · University of Central Punjab
Plan · Build · Review · Improve
Notes: Welcome. Today we turn Project Goal 1 into practice: how Scrum works, how to write a backlog in Jira, and a worked case study of a team re-engineering the Student Result Management System. By the end, every team should know exactly what their Jira project must contain by Week 4.

## Slide 2: Milestone 1 at a glance
25+
user stories with criteria and points, by Week 4
5
two-week sprints, Weeks 5 to 15
10
logged events: 5 sprint reviews + 5 retrospectives
30%
of the project mark is the Agile process in Jira
Goal 1 (SMART): By Week 4, a Jira backlog of 25+ user stories with acceptance criteria and story points; then five 2-week sprints by Week 15, each with a logged review and retrospective.
Notes: Read the SMART goal aloud and point out each measurable number. Specific: a Scrum backlog for your system. Measurable: 25 stories, 5 sprints, 10 logged events. Achievable on the free Jira plan. Relevant: the backlog drives the Claude Code work. Time-bound: Week 4 and Week 15. The Agile component is 30% of the 10% project weight.

## Slide 3: Why Agile suits legacy re-engineering
Waterfall
Plan once, at the start
Requirements frozen in a long SRS
Working software only at the end
Feedback at acceptance testing
Hidden legacy debt breaks the plan
Scrum
Re-plan every 2 weeks
Living backlog, ordered by value
A working increment every sprint
Feedback at every sprint review
Legacy debt becomes backlog items
Notes: In re-engineering, requirements are discovered while reading old code. Waterfall assumes we know everything upfront; the first surprise in the legacy code breaks the plan. Scrum expects surprises: anything we discover becomes a backlog item and is planned in the next sprint. Ask the class: what surprises might hide in a 10-year-old Java Swing app?

## Slide 4: The Agile Manifesto: four values
1
Individuals and interactions
over processes and tools
In class: talk first, then record it in Jira.
2
Working software
over comprehensive documentation
In class: a working demo at every sprint review.
3
Customer collaboration
over contract negotiation
In class: your instructor is the stakeholder.
4
Responding to change
over following a plan
In class: re-order the backlog every sprint.
Notes: The Agile Manifesto (2001) does not say the items on the right are worthless. You will still produce UML, ERDs and reports in this course; they simply serve the working software. Ask students which value they think is hardest for a student team.

## Slide 5: The Scrum framework
PART 1
3 · 5 · 3
roles · events · artifacts
Notes: Scrum is a lightweight framework with a simple shape: three roles, five events and three artifacts. Students should be able to recite 3-5-3 for the quiz.

## Slide 6: Three roles, rotating every sprint
Product Owner
OWNS
What gets built, and in what order: the product backlog.
IN THIS COURSE
Writes and orders stories in Jira. Rotates each sprint.
Scrum Master
OWNS
How the team works: ceremonies and removing blockers.
IN THIS COURSE
Runs planning, review and retro; checks stand-up comments.
Developers
OWNS
Building a Done increment every sprint.
IN THIS COURSE
The whole team, PO and SM included, working with Claude Code.
Notes: Stress that PO and SM rotate every sprint, so each student practises both. With five sprints and a team of four or five, everyone plays PO once and SM once. Record the rotation in the sprint goal field in Jira so the instructor can verify it.

## Slide 7: The 2-week sprint cycle
Product backlog
Ordered by the PO
Sprint planning
Pick stories, set the sprint goal
Sprint (2 weeks)
Stand-ups as Jira comments, twice a week
Sprint review
Demo the increment, log feedback
Retrospective
Improve how we work next time
next sprint
Output of every sprint: a working, tested Increment that meets the Definition of Done and can be demoed.
Notes: Walk the loop left to right. In our course the daily scrum is replaced by stand-up comments in Jira twice a week: what I did, what I will do, what blocks me. The review is a demo to the instructor; the retrospective is the team talking about its own process. Both must be logged in Jira. Then the loop repeats from planning.

## Slide 8: Three artifacts, three commitments
Product Backlog
Ordered list of everything Version 2.0 needs
COMMITMENT
Product Goal
Sprint Backlog
Stories picked for this sprint, plus the plan
COMMITMENT
Sprint Goal
Increment
Working, tested, deployed software at sprint end
COMMITMENT
Definition of Done
Notes: Each artifact has a commitment that gives it focus. For example, your Product Goal could be: SRMS Version 2.0 live on the web by Week 15. Every sprint needs a one-sentence Sprint Goal, typed into Jira when you start the sprint.

## Slide 9: Building the backlog
PART 2
stories · criteria · points · Done
Notes: Part 2 covers the four things every backlog item needs: a well-formed story, acceptance criteria, story points, and the shared Definition of Done.

## Slide 10: Anatomy of a user story
As a student, I want to view my semester GPA online so that I don't have to visit the exam office.
WHO
As a <role>
A real user or stakeholder: student, teacher, exam officer, maintainer.
WHAT
I want <goal>
One capability, small enough to finish in one sprint.
WHY
so that <benefit>
The value. It is how the PO decides the order of the backlog.
Notes: Every story uses the same three-part template. The 'so that' part is the one students skip most often, but it is what lets the Product Owner order the backlog by value. A story without a benefit is usually a task in disguise.

## Slide 11: INVEST: test every story
I
Independent
Deliverable on its own
Red flag: “needs SRE-14 and SRE-22 first”
N
Negotiable
Open to discussion on how
Red flag: a full technical design inside
V
Valuable
Useful to a user or stakeholder
Red flag: “refactor class X” with no benefit
E
Estimable
The team can size it
Red flag: nobody can explain it
S
Small
Fits one sprint: 8 points or less
Red flag: 13 points or more
T
Testable
Has clear pass / fail checks
Red flag: “the system should be fast”
Notes: Use INVEST as a quick review checklist during backlog refinement in Week 4. The two most common failures in student backlogs are Small (epics disguised as stories) and Testable (vague quality words). Anything 13 points or more must be split before it enters a sprint.

## Slide 12: Acceptance criteria: Given / When / Then
Happy path
Given I am logged in as a student
When I open “My Results” for Fall 2026
Then I see each course, its grade and my GPA to 2 decimals
Unhappy path
Given my results are not yet published
When I open “My Results”
Then I see “Results not yet published” and no grades
Write 2–4 criteria per story in the Jira description, and always include at least one unhappy path.
Notes: Acceptance criteria define when ONE story is finished from the user's point of view. Given sets the context, When is the action, Then is the observable result. Push students to include edge cases: unpublished results, wrong passwords, empty files. These later become their test cases.

## Slide 13: Story points: relative, not hours
1
Fix a label on the login screen
2
Validate the roll number field
3
Student views own result card
5
Admin uploads marks from CSV
8
Extract DAO layer from Swing forms
13
Too big: split it before the sprint
Planning poker in five steps
1
PO reads the story and its criteria
2
Team asks questions (2 minutes)
3
Everyone reveals a card at once
4
Highest and lowest explain why
5
Re-vote once; type it into Jira
Notes: Points measure effort, complexity and uncertainty relative to other stories, never hours. The gaps grow because bigger work is harder to predict. In legacy systems, step 4 of planning poker is where hidden risks come out: the person voting 8 often knows something about the old code the person voting 2 does not.

## Slide 14: Velocity and the Definition of Done
Velocity
Points of stories that are Done in the sprint
8 + 5 + 5 = 18
A 3-point story that is 90% done counts as 0.
Plan each new sprint from the average velocity of the last three sprints.
Definition of Done (every story)
Code reviewed through a GitHub pull request
Tests pass
Linked to its Jira issue
Deployed to staging (from Sprint 4)
Documentation updated
Criteria are per story; Done applies to all. Both must pass.
Notes: Velocity only counts Done work, so partially finished stories do not inflate it. Students should never inflate points to look fast; the instructor grades consistency. The Definition of Done comes straight from the course outline's Agile working agreement.

## Slide 15: Every commit carries its Jira key
Branch feature/SRE-12-result-view
Commit SRE-12 Add results REST endpoint
Commit SRE-12 Add unit tests for GPA
PR SRE-12 Student can view results
Jira's Development panel shows the code behind each story.
Meets the course AI-use rule: every Claude Code change is traceable.
Set up once: Jira → Apps → GitHub for Jira, link your repo.
Tip: paste the story and its criteria into your Claude Code prompt, and ask it to start every commit message with the key.
Notes: The course outline says every AI-assisted change is committed under the team's Jira issue. The simplest way is a naming convention: the Jira key at the start of the branch, every commit and the pull request title. Demonstrate the GitHub for Jira app live if lab time allows.

## Slide 16: Jira setup in six steps
1
Create project
Scrum template, team-managed, key SRE
2
Invite people
Whole team, plus the instructor as Viewer
3
Turn on points
Project settings → Features → Estimation
4
Epics → stories
Summary, Given/When/Then, points, labels
5
Order and start
PO orders backlog; start sprint with a goal
6
Run and report
Board, stand-up comments, burndown, velocity
Stand-up comment, twice a week on your active issue
Done: extracted StudentDAO (SRE-15) · Next: DAO unit tests · Blockers: MySQL 5 dump fails on MySQL 8
Notes: Do these steps live in the lab with one team's laptop on the projector. Menu names may shift as Atlassian updates the free plan, so show students how to search settings. Step 5 is highlighted because the PO's ordering decision is the heart of Scrum. Close a sprint with Complete sprint; unfinished stories return to the backlog.

## Slide 17: The semester in sprints
Discovery + backlog
Weeks 1–4
25+ stories, A0–A3
Sprint 1
Weeks 5–6
Reverse UML
Sprint 2
Weeks 7–8
Architecture
Sprint 3
Weeks 10–11
ERD + API
Sprint 4
Weeks 12–13
AI + refactor
Sprint 5
Weeks 14–15
Go live
Mid-term
v2.0
Wk 16
Demo
Backlog ready
Mid project review
v2.0 live
Peer redeploy + final demo
Each sprint: planning in its first week, review + retrospective in its second. No sprint in mid-term Week 9.
Notes: This is the calendar from Section C of the outline. The orange diamond is today's milestone: the backlog must be ready at the end of Week 4, before Sprint 1 planning. Point out the assessments each sprint delivers, so students see the backlog is not separate from the re-engineering work; it schedules it.

## Slide 18: Student Result Management System
PART 3 · CASE STUDY
Java Swing + MySQL v1.0 → web v2.0
Notes: The case study uses the SRMS v1.0 example named in the outline. The team (Ayesha, Bilal, Hamza and Sana) and all numbers are fictional and for illustration only; students should use it as a model, not copy it.

## Slide 19: SRMS v1.0 today, v2.0 target
Aspect | v1.0 today | v2.0 target
Platform | Java Swing desktop on exam-office PCs | Web app at a live URL
Data | MySQL 5; SQL inside form classes | DAO layer + REST API on MySQL 8
Users | Exam office staff only | Students, teachers and exam office
Tests | None | Unit tests + Postman collection
Documentation | None; original developer left | UML, ERD and a deployment README
Illustrative case study based on the outline's SRMS v1.0 example (Java Swing and MySQL).
Notes: Ask the class to name the stakeholder who suffers from each v1.0 problem. Students cannot see results; teachers re-enter marks; the IT maintainer cannot change the database. Each pain becomes an epic on the next slide.

## Slide 20: 26 stories, 86 points, six epics
Chart: Story points per epic (stories in brackets)
| E1 Accounts & login (4) | E2 Result entry (5) | E3 Result viewing (4) | E4 Transcripts (4) | E5 Migration (5) | E6 Deploy & NFRs (4)
Story points | 13 | 18 | 11 | 15 | 21 | 8
21
points in E5, the tech-debt epic: the largest in the backlog
Re-engineering work is backlog work. Plan it, size it and demo it like any feature.
Notes: The team interviewed four stakeholders: students, teachers, the exam office and the IT maintainer. Each need became an epic. Highlight that the biggest epic is the maintainer's: migration and the legacy wrapper. In re-engineering, technical debt is not hidden work; it is planned in the backlog.

## Slide 21: A tech-debt story drives Claude Code
SRE-15 · 8 points · tech-debt
As a maintainer, I want SQL moved out of Swing forms into DAO classes so that the database can change without UI edits.
Given the legacy ResultForm and StudentForm
When the DAO refactoring is merged
Then neither form contains an SQL string
And every v1.0 screen saves and loads the same data
Claude Code prompt
Story SRE-15 (paste the story text)
Acceptance criteria (paste Given/When/Then)
First list every SQL string in src/forms
and propose a DAO design.
Wait for my approval, then refactor
one form at a time.
Start every commit message with SRE-15.
Review every change in a pull request: each student explains this code in the Week 16 viva.
Notes: This is the link between Goal 1 and Goal 2. The story and its criteria become the prompt. Asking Claude Code to plan first and wait for approval keeps students in control, and the commit prefix keeps the work traceable in Jira. Remind students they must be able to explain AI-written code in the final viva.

## Slide 22: Sprint 1 review and retrospective
Review: demoed the Mermaid class diagram and the DAO layer. The instructor asked for a sequence diagram of result entry, so the PO added SRE-31.
Went well
Every commit carried its Jira key. Claude Code mapped all 40 legacy classes in one session.
Didn't go well
The database blocker sat in one person's head for a day before reaching a stand-up comment.
We will change
Raise any blocker in Jira the same day. Plan 18 points for Sprint 2, not 21.
Notes: The review looks at the product; the retrospective looks at the team. Notice that the review produced a new backlog item (SRE-31) and the retro produced a concrete change in planning (18 points). Both are logged in Jira as a Task called 'Sprint 1 Review & Retro'.

## Slide 23: Your turn: a 20-minute mini backlog
20
minutes
2 min
Choose the main user of your team's legacy system.
8 min
Write three user stories using the template.
5 min
Add Given / When / Then, with one unhappy path each.
5 min
Planning poker with the team next to you.
Then enter them in Jira tonight: they count toward your 25+.
Notes: Run this as a timed in-class exercise. Walk around and check the 'so that' clauses and the unhappy paths. During planning poker, ask the team next door to estimate, so students learn to write stories that strangers can understand.

## Slide 24: Before Week 4: your backlog checklist
Jira Scrum project; team and instructor invited
5–8 epics, each tied to a stakeholder
25+ stories in the As a / I want / so that form
2–4 Given/When/Then criteria per story
Story points on every story; none above 8
Labels: tech-debt and nfr where they apply
Backlog ordered; Sprint 1 PO and SM named
GitHub linked; a test commit shows in Jira
Next class: Sprint 1 planning. Bring your ordered backlog.
Notes: Close by reading the checklist. This is what will be checked at the end of Week 4 under the 'backlog quality' part of the Agile grade. Remind teams that next class starts Sprint 1 planning, so they must arrive with an ordered backlog.